## Blank Charter
Project Title: | See Next Tabs in Excel Worksheet for Section Descriptions & Sample Charters. Please Download the File & Save with a New Name to your computer.
Business Case:
Problem / Opportunity Statement:
Goal Statement:
Project Scope:
Sponsor: |  |  |  | Stakeholders:
Project Leader:
Project Black Belt:
Team Members:
Preliminary Plan | Target Date | Actual Date | Estimated Cost Savings:
Start Date:
DEFINE
MEASURE
ANALYZE |  |  | Notes:
IMPROVE
CONTROL
Completion Date:

## Charter w Section Descriptions
Project Title: | Project Title
Business Case: | Provide a broad overview of the issue assigned to the team, as well as the rationale for why this particular project should be a key business priority.
Problem / Opportunity Statement: | One or two sentence description of the symptoms arising from the problem to be addressed.
It will often parallel the Business Case, but will be more specific and focused. Answer; What’s wrong? Where is the problem appearing?
How big is the problem? What is the impact of the problem on the business? (SMART) Specific Measurable Achievable Relevant Time Based
Goal Statement: | Goal Statement and Problem Statements are a matched pair. Includes a description of what is to be accomplished (reduce, increase, eliminate), a measurable target for desired results, and a projected completion date to reach the goal (SMART) Specific Measurable Achievable Relevant Time Based
Project Scope: | Outline the project scope in process terms (SIPOC - where does it start and stop), and identify constraints and assumptions. How long can the project take? Is there a deadline? How much of our work time can be devoted to project per week? Do we have any authority to spend money? Who (what) are our internal/external resources? What is not in the scope.
Sponsor: |  |  |  | Stakeholders:
Project Leader: |  |  |  | The people who can influence or are affected by your project, both internal and external to your organization.
Project Black Belt:
Team Members:
Preliminary Plan | Target Date | Actual Date | Estimated Cost Savings: Identify potential financial impact and then realized impact after completion of the project. Cost reduction (typically labor time and materials), cost avoidance, increased Sales $, increased $/unit, etc.
Start Date:
DEFINE
MEASURE
ANALYZE |  |  | Notes: Capture Lessons Learned. Things Gone Right. Things Gone Wrong.
IMPROVE
CONTROL
Completion Date:

## BoxVanCharter
Project Title: | Box Van Kaizen Improvement Project
Business Case: | • There is large potential for growth in the Box Van market.
• Decreasing the material and production time & costs will be beneficial as we penetrate this market.
Problem / Opportunity Statement: | • Although there has been success with the Box Van current design & processes, we may be able to find ways to produce them at less cost in less time.
• If we reduce materials cost and reduce process time and costs, we may be able to make more profit per Box as well as more Boxes with the same amount of resources & time.
Goal Statement: | Reduce the material & production costs by $250; stretch goal $500.
Reduce the time to produce by 2 hrs; stretch goal 4 hrs by 12/25/2016.
Project Scope: | • Alter the design in order to: - Eliminate any parts or material costs possible - Reduce or simplify the remaining as much as possible with respect to process time & costs - While keeping the features valued by the customer. • Find any lower cost alternatives to materials & components as well as the best prices on them. • Analyze the fab, assembly, and installation processes for improvements that could reduce time & processing costs. • Document the refined processes for standardization and training.
Sponsor: | James McDowell |  | Josh Whited | Stakeholders:
Team Leader: | Nolan Mullin |  | Daniel Miller | Ownership, Rob Overholser, Hardie Harris, Eric James, Nathan Wall, James McDowell, Tim Pike, Russ Hartz, Josh Reed, Box Van Workers & Mgt, Materials Handlers, Engineering, Purchasing, Product Support, Quality Team, Suppliers, & Customers
Black Belt: | Adam Druffel & Michael Asbury |  | Walt Williams
Team Members: | Greg Teel |  | Jordan Reese
| Russ Boozer |  | Russ Hartz
Beth Katenin
Preliminary Plan | Target Date | Actual Date | Estimated Cost Savings: (Need Baseline Data) Materials Savings: $115 to $230 (Elimination/Reduction/Simplification/Alternatives/Price Reductions) Process Time Savings: ~$135 to $270
Start Date: | 2016-06-28
DEFINE | 2016-06-28
MEASURE | 2016-06-29
ANALYZE | 2016-06-29 |  | Notes: Daily Report Out Meetings 4pm to Mgt & Final Report Out 2-3pm 5/27 Capture Lessons Learned. Things Gone Right. & Things Gone Wrong.
IMPROVE | 2016-06-30
CONTROL | 2016-06-30
Completion Date: | 2016-07-01

## EastLotCharter
Project Title: | East Lot Visual Process Management Project
Business Case: | • Over the last several years the volume and complexity of the product mix continues to increase.
• Successfully managing the flow of inbound & outbound materials is challenging and CRITICAL to ensuring that everything needed is available when needed to add & deliver value to our customers as promised.
Problem / Opportunity Statement: | •The target area is disorganized, full of materials, many of them are damaged or obsolete, and it is a high traffic area with blind spots and traffic jams.
• There is not much room to receive parts that are being staged in the area & currently not utilizing vertical storage potential. Finding the parts needed requires searching and moving parts out of the way.
• Systematic organization could reduce time & effort required to efficiently & effectively manage the flow while reducing clutter, damage (rework & scrap), and safety risks.
Goal Statement: | • Re-organize east lot area to create an intuitive visual flow management system structured to reduce effort to place and retrieve materials without damage.
• Reduce resource time consumed searching for and moving materials in the area by 30%, number of obsolete parts in the area to 0, and reduce parts damage by 90% by 7/1/2016
• Reduce blind spots & traffic jams to provide a safer, more professional & visually appealing working environment free of trash & clutter, achieve 6S score >70 by 5/27/2016
Project Scope: | • The target area is the East Lot temporary hold area where inbound, WIP, Finished Goods, outbound, and materials racks are temporarily held prior to the next processes. • Within 5 LONG Work Days (6am - 4pm), 6S is to be implemented in the area: • SORT: Unneeded, damaged, & obsolete items will be removed for final disposition, • SHINE: Clean the area & remove trash, etc • SET-IN-ORDER: Set strategically designated areas for anything needed there Using visual controls: signage, labels and boundary lines (Location System???) • STANDARDIZE & SUSTAIN: Processes and audits will be established with roles, responsibilities, & frequencies of duties defined, communicated, & trained • SAFETY: Risks will be identified & removed and Warning Signs appropriately placed. • Team members will be focused full time on this project during the week. • An action log of assignments will be used to track follow up items. • Resources: Maintenance, IT, Purchasing, Tow Motor w/ Driver, • Budget: $2,500 before seeking additional approval • Target Area is from Paint Room to North side of 30th St drive intersection & entrance to Street.
Sponsor: | Harry Marcionetti |  | Mike Francis | Stakeholders:
Team Leader: | Collin Stevenson |  | Rob Garkie | Ownership, Harry Marcionetti, Nathan Wall, Dale Gill, Collin Stevenson, Kent Kite, Kent Dade, Trim Workers & Mgt, Finish Workers & Mgt, Shipping Workers & Mgt, Materials Handlers, PIC, Purchasing, Suppliers, & Customers
Black Belt: | Michael Asbury |  | Brooks Bainter
Team Members: | Blake Calvert |  | Ryan Gilbert
| Chuck Jackson |  | Brody Gronewald
| David Wallace |  | Levi Kirby
Preliminary Plan | Target Date | Actual Date | Estimated Cost Savings: (Need Baseline Data) YTD Damage Costs, Time to Find Parts, Time to Retrieve parts after moving parts to get to desired parts, number of blindspots, amount of traffic jams, number of damaged & obsolete parts, Current 6S score, time to pick up empty racks and drop off full from suppliers, wait time for loads
Start Date: | 2016-05-23
DEFINE | 2016-05-23
MEASURE | 2016-05-23
ANALYZE | 2016-05-23 |  | Notes: Daily Report Out Meetings 4pm to Mgt & Final Report Out 2-3pm 5/27 Capture Lessons Learned. Things Gone Right. & Things Gone Wrong.
IMPROVE | 2016-05-26
CONTROL | 2016-05-27
Completion Date: | 2016-05-27